Neighbourhood Plan Process: Timeline and Progress

| Stage 1: Getting Established & Area Designation | Completed 2023 |
| --- | --- |
| - Form a Qualifying Body: If a town or parish council exists, they will lead, advised by a Steering Group - Define the Boundary: Submit a map and application to your local planning authority (LPA) to designate the physical boundary of your neighbourhood area. The LPA will hold a consultation period before formally approving it | Sept 3rd 2023 - Dec 2023 July 14th 2023 |

| Stage 2: Building the Evidence & Community Engagement | Completed 2025 |
| --- | --- |
| - Gather Evidence: Collect local data, assess housing and environmental needs, and review existing national and local planning policies - Consultation: Engage the wider community via surveys, public displays etc | Feb 2024- March 2024 March 2024-Nov 2025 |

| Stage 3: Drafting the Plan and consultation | In progress |
| --- | --- |
| - Set Objectives & Policies: Formulate a vision statement and clear planning policies for land use (e.g., where new homes should go, design standards, preserving green spaces) - Pre-Submission Consultation: Share the draft plan with the community, statutory consultees (e.g., Environment Agency), and local businesses for a minimum of six weeks - Adjust the plan based on the feedback - Consult on the revisions | Jan 2026 March 26th – May 14th 2026 Started June 2026 Estimated July to Sept 2026 |

| Stage 4: Submission & Independent Check | Estimated Sept/Oct 2026 |
| --- | --- |
| - Submit to the LPA: The qualifying body submits the final proposal, a consultation statement, and a "basic conditions" statement to the local council - Independent Examination: The LPA appoints an independent examiner to check that the plan meets national policies and legal requirements |  |

| Stage 5: Referendum, Adoption, and Legal Force | Estimated 2027 |
| --- | --- |
| - Community Referendum: The local council organizes a public vote. If more than 50 percent of residents who vote approve the plan, it passes - Adoption (Made): The local authority formally adopts the plan. It then becomes a legal document that carries full weight in deciding local planning applications but does not replace planning applications |  |